## Sheet1
Project Name: Online PoS System for Railway Ticket
Project Start Date: | 2024-11-14
Current Date: | 2024-12-16
Project End Date | 2024-12-20
Weeks in Progress: | 5
[6 empty] | November | [16 empty] | December
Task | Project Lead | Start Date | End Date | Days | Progress | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6
[6 empty] | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20
Requirement Analysis | [42 empty] | Submission
Booking and Reservation System | Arif Jewel | 2024-11-14 | 2024-11-15 | 2 | 100%
Payment Processing System | Fahad Muhammad | 2024-11-14 | 2024-11-22 | 9 | 100%
User and Admin Management | Arif Jewel | 2024-11-14 | 2024-11-22 | 9 | 100%
Top-Level Design
System Architecture Design | Arif Jewel | 2024-11-21 | 2024-11-29 | 9 | 100%
User Interface & User Experience Design | Arif Jewel & Fahad Muhammad | 2024-11-21 | 2024-11-29 | 9 | 100%
Secure Payment and Data Design | Fahad Muhammad | 2024-11-21 | 2024-11-30 | 10 | 100%
Detailed Design
Use-Case Diagram | Fahad Muhamma | 2024-11-21 | 2024-11-23 | 3 | 100%
Class-Case Diagram | Arif Jewel | 2024-11-21 | 2024-11-28 | 8 | 100%
Sequence Diagram | Arif Jewel | 2024-11-21 | 2024-11-28 | 8 | 100%
Implementation & Unit Testing
System Integration and Configuration​ | Arif Jewel | 2024-11-28 | 2024-12-05 | 8 | 100%
Testing and Quality Assurance | Fahad Muhammad | 2024-11-28 | 2024-12-12 | 15 | 100%
Deployment and User Training | Arif Jewel | 2024-11-28 | 2024-12-15 | 18 | 100%
Integration Testing
Component Interaction | Arif Jewel & Fahad Muhammad | 2024-12-05 | 2024-12-18 | 14 | 100%
Interface Testing | Arif Jewel & Fahad Muhammad | 2024-12-05 | 2024-12-18 | 14 | 100%
Error Handling | Arif Jewel & Fahad Muhammad | 2024-12-05 | 2024-12-18 | 14 | 100%